## Timeline
| To Focus On | To-Do | Labor Status
Week 1 | STLYES DEVELOPMENT AND MARKETING PLAN | moodboard, timeline backwards from launch date, one page business plan
Week 2 | CUSTOMER RESEARCH AND COMPETION | sketches developed, do your customer and competitor research start to develop a plan of action to get in front of them, do an estimated costing sheet to work from (fabirc costs, etc.)
Week 3 |  | confirm sketches and assign style numbers | size chart determined
Week 4 | FABRIC SELECTION | fabric swatching | pattern and sample estimate
Week 5 | LOGO FOR BRANDING | labels, logos, hangtag designs started | first patterns started
Week 6 | MARKETING PLAN MADE | order labels, hangtags, once you have your logo start your online presence
Week 7 | PATTERN DEVELOPMENT |  | first patterns finished
Week 8 |  |  | prototypes started
Week 9 |  | hire a fit model | prototypes finished
Week 10 | FITTING AND FABRIC SELECTION | confirm fabric selection and order fabric for samples | 1st prototype fitting
Week 11 |  | book fit model | pattern alts
Week 12 |  | wash test your fabric | 2nd proto fitting
Week 13 |  | book fit model and order care labels | finish patterns and start samples
Week 14 |  | hire fit model | samples created
Week 15 |  | start to look into photographers and models for shoot | samples fitting
Week 16 | PHOTOSHOOT | photoshoot of samples | tech packs
Week 17 | MANUFACTURING | manufacturing quotes | patterns digitized for size check run
Week 18 |  | yields created from digital files and fabric ordered for size check run | markers created for size check run
Week 19 |  | make maketing material from photoshoot, snail mail postcard, line sheets, upload on to website and costing completed | size check run at the manufacture
Week 20 |  | book your fit models for multiple sizes
Week 21 |  | send out your postcards to boutiques, calling them before they go out and after | fitting for size check run
Week 22 | SELLING PLAN ESTABLISHED VIA WHOLESALE (Feb for Fall and August for Spring) | generate sales from your samples, create your sales plan of attack (set up selling opportunities) wholesale tradeshows, on the road selling, pursing sales reps) | markers created for production run
Close selling date |  | order production run fabric
|  | oversee production | production run started at manufacture
oversee production
Aug/Sep for FALL and Feb/March for SPRING |  | delivery to stores
WHILE SELLING ONE SEASON START PROCESS OVER FOR SECOND | SELLING DIRECT TO CUSTOMER | selling avenues, shows, tradeshow, trunk shows, home show, website, etc, | production run completed