Proposed Timetable Hikurangi Sports Collective

| Date0Meeting Focus / Agenda |  | Outcomes |  | Who |  |
| --- | --- | --- | --- | --- | --- |
| Mon 23rd November | Determination of a Chair for meetings Agreement on secretarial support Confirmation of the need for a monthly communications process back to the clubs to their next committee meeting by their representative (Elected Sec to forward all info to Club Committees, and Info to be posted to Hika Website.) Development/Review of Project Schedule of Terms of Reference for Working Group to establish a unifying entity. Adopt Project Plan |  | Chair elected from WP Secretarial support confirmed Communication process confirmed with Club representatives Project Schedule adopted |  |  |
|  | of Terms of Reference for Working Group to establish a unifying entity. Adopt Project Plan Feedback from clubs considered and adopt TOR Discuss and develop draft Objects |  | Adopt TOR Draft Objects developed and sent to Clubs for comment prior to next meeting |  |  |
| MON 5th December | Feedback from Clubs considered on Draft Objects (review balance of document if time permits) |  | Draft Objects adopted (agreed changes made to balance of document or clauses adopted without change) |  |  |
| MON 13th February | Discuss membership (founding, affiliate etc) and Board composition and develop draft clauses for discussion |  | Draft membership and Board composition clauses sent to clubs for comment prior to next WP meeting I would just send them the constitution including the updated objects |  | Peter Burley to attend /skype |
| MON 12th March | Feedback from clubs considered on draft membership and Board composition clauses Review and amend balance of draft constitution |  | Adopt draft membership and Board composition clauses Draft Lindvart Park constitution complete and available to present to clubs |  |  |
| MON 9 th April | Each club holds meetings with their membership to ratify the developed constitution. |  | Meetings held, constitution ratified by member clubs Letter sent to the working party confirming acceptance into Lindvart Sportsville Inc by Mon 14th May. (draft attached for you to sedn out to the clubs with the constitution Formalise and register the new body as an incorporated society |  | League, Soccer, Hockey, Netball, Basketball Clubs |
| Mon 14th May | Develop Board Member profile, advertise the positions and actively seek people to consider becoming members of the Board. Identify a selection panel and process and to screen applicants appropriately and determine an inaugural board for the new entity |  | Board member profile developed and content of adverts confirmed. Selection panel appointed, process confirmed for short listing and interviews |  |  |
| Mon 11th June | Inaugural Board meeting, election of community representatives and WP constituted as a committee of the Board. |  | Full Board elected WP constituted as a committee of the Board (optional) |  |  |